## Sheet1
User Storys:
100 points | As a user, I want to create and sign in with their school emails
20 points | As a tutor, I want to sign up to become a tutor on the app and change my setting if I make a mistake
20 points | As a user, I want to see the available tutors
20 points | As a user of the app, I want to be able to change my settings, so that I can fix any mistakes I made during the signup process
Meetings | Total points | Completed points that meeting
1 | 0 | 0
2 | 40 | 40
3 | 60 | 20
4 | 90 | 30
5 | 112 | 22
6 | 147 | 35
Total Points | 147
Goal Line for Graph
1 | 160
2 | 160
3 | 160
4 | 160
5 | 160
6 | 160