## Sheet1
User Storys:
5 points | As a user, I want to be able to upload a profile picture and my transcript for verification
10 points | As a user, I want to filter classes by departments so I don't waste time searching for a course
10 points | As a user, I want to be able to have a pleasing theme to view on the page
45 points | As a user, I want the ability to search for tutors specific to a course
Meetings | Total points | Completed points that meeting
1 | 0 | 0
2 | 10 | 10
3 | 40 | 30
4 | 45 | 5
5 | 70 | 25
6 | 70 | 0
Total Points | 70
Goal Line for Graph
1 | 70
2 | 70
3 | 70
4 | 70
5 | 70
6 | 70